## Stone Wall Measurements
GRG INFRA PVT LTD
CONTRACTOR: | PAWAN KUMAR |  | COMPANY NAME: | ADITYA CONSTRUCTION COMPANY
LAST UPDATED: | 21/07/2026
RUNNING BILL FRIST
SECTION 1: RECORD DATE - 09/06/2026
S.No | Work Description | Length (L) in ft | Width (W) in ft | Height/Depth (H) in ft | P.C.C. Area (Sq.Ft) | Stone Volume (Cu.Ft) | Remarks / Handwritten Value
1. डिगी दीवार (Diggi Wall)
1.1 | P.C.C. | 126.28 | 3 | 0.333 | 378.84 | - | 378.84 Sq.Ft
1.2 | Stone Work | 74.78 | 2 | 3 | - | 448.68 | 448.70 Cu.Ft (Calculated: 448.68)
1.3 | Stone Work | 37.72 | 2 | 1.5 | - | 113.16 | 113.16 Cu.Ft
2. बाउंड्रीवाल कार्य (Boundary Wall Work)
2.1 | P.C.C. | 268 | 2.5 | 0.333 | 670 | - | 670.00 Sq.Ft
2.2 | Stone Work | 268 | 2 | 1 | - | 536 | 536.00 Cu.Ft
2.3 | Stone Work | 252 | 1.5 | 2 | - | 756 | 756.00 Cu.Ft
2.4 | P.C.C. | 295 | 2.5 | 0.333 | 737.5 | - | 737.50 Sq.Ft
2.5 | Stone Work | 295 | 2 | 1 | - | 590 | 590.00 Cu.Ft
2.6 | Stone Work | 101 | 1.5 | 2 | - | 303 | 303.00 Cu.Ft
TOTAL P.C.C. AREA (SECTION 1) |  |  |  |  | 1786.34 | Sq.Ft | Handwritten: 1785.84 Sq.Ft
TOTAL STONE WORK VOLUME (SECTION 1) |  |  |  |  | Cu.Ft | 2746.84 | Handwritten: 2746.86 Cu.Ft
RUNNING BILL SECOND
SECTION 2: RECORD DATE - 09/07/2026
S.No | Work Description | Length (L) in ft | Width (W) in ft | Height/Depth (H) in ft | P.C.C. Area (Sq.Ft) | Stone Volume (Cu.Ft) | Remarks / Handwritten Value
3. बाउंड्रीवाल नया कार्य (Boundary Wall New Work)
3.1 | P.C.C. | 1000 | 2.5 | 0.333 | 2500 | - | 2500 Sq.Ft
3.2 | Stone Masonry | 1000 | 2 | 1.5 | - | 3000 | 3000 Cu.Ft
3.3 | Stone Masonry | 1000 | 1.5 | 1.5 | - | 2250 | 2250 Cu.Ft
TOTAL P.C.C. AREA (SECTION 2) |  |  |  |  | 2500 | Sq.Ft | Calculated: 2,500.00 Sq.Ft
TOTAL STONE WORK VOLUME (SECTION 2) |  |  |  |  | Cu.Ft | 5250 | Calculated: 5,250.00 Cu.Ft
GRAND COMBINED TOTALS (ALL RECORDS)
GRAND TOTAL P.C.C. AREA (SECTION 1 + 2) |  |  |  |  | 4286.34 | Sq.Ft | Combined PCC Area
GRAND TOTAL STONE WORK VOLUME (SECTION 1 + 2) |  |  |  |  | Cu.Ft | 7996.84 | Combined Stone Volume
SECTION 1 AUDIT: HANDWRITTEN VS. SYSTEM CALCULATED
Item Category | Handwritten Value | Formula Calculated | Difference | Audit Note / Analysis
Diggi Wall Stone (Item 1.2) | 448.7 | - | #VALUE! | 74.78 * 2.0 * 3.0 equals 448.68 cft. Rounded to 448.70 in diary.
Total P.C.C. Area | 1785.84 | 1786.34 | -0.5 | Handwritten total sum used '737' instead of '737.50' (omitted 0.5 sqft).