## PO & Payment Tracker
KHAVDA 442MW SOLAR PROJECT — VENDOR PO & PAYMENT TRACKER
PROJECT: KHAVDA 442MW ¦ DOCUMENT TYPE: RECONCILED PO & VENDOR PAYABLE STATEMENT ¦ DATE: 29-07-2026
| TOTAL VENDORS |  |  | TOTAL PAID AS ON DATE |  |  | TOTAL OUTSTANDING PAYABLE |  |  | TOTAL CONTRACT VALUE |  | OVERALL PAID RATIO
S.No. | Ref Sr. | PO Number | Project Name | Type | Description / Scope | Company / Vendor Firm Name | Vendor Contact / Representative | Paid As On (₹) | Amount to be Paid (₹) | Total Value (₹) | Paid % | Payment Status | Audit / Highlight Notes
1 | 8 | 6002526032 | KHAVDA 442MW | Service | Piling Work | VIBRANT CONSTRUCTION COMPANY | Mohamad (6360589955) | 8142757 | 500000
2 | 16 | 6002526062 | KHAVDA 442MW | Service | Erection of MMS | Murlidhar Fabrication | Suresh Kumar (+91 99783 01708) | 2684889 | 1460059
3 | 17 | 6002526026 | KHAVDA 442MW | Service | Erection of MMS | Choudhary Electric Constrution | Sarvan Choudhary +91 90013 29239 | 8361290 | 2507431
4 | 22 | 6002526025 | KHAVDA 442MW | Service | Supply Of White Sand | R.K.PROJECT | GAGAL RAMESHBHAI (+91 6354263514) | 5216596 | 24170
5 | 24 | 6002526050 | KHAVDA 442MW | Service | DG | PALIWAL BUILDING MATERIAL | Lalit- | 1606082 | 250000
6 | 25 | 6002526051 | KHAVDA 442MW | Service | HT Cable laying | SUPER ELECTRO POWER POONA RAM | Poona ram | 3817310 | 213861
7 | 27 | 6002526061 | KHAVDA 442MW | Service | VLF Testing | TNM GENIE PRIVATE LIMITED | Saravanakkumar +91 9741402787 | 664070 | 44314 |  |  |  | Highlighted Yellow in Statement
8 | 31 | 6002526072 | KHAVDA 442MW | Service | Erection of MMS | PUSHPA ENTERPRISES | RAM KUMAR (+91 97259 87924) | 2426646 | 222850
9 | 15 | 6002526084 | KHAVDA 442MW | Service | Erection of MMS | R P CONSTRUCTION | BAYUNANDAN PANDE (92419 50137) | 1651357 | 35435
10 | 17 | 6002526087 | KHAVDA 442MW | Service | Erection of MMS | AKSHAR CORPORATION | MEHULKUMAR VASUDEVBHAI PATEL | 2636044 | 456175
11 | 19 | 6002526091 | KHAVDA 442MW | Service | Erection of MMS | ADITYA POWER TECHNOLOGIES | Hemang Patel | 620240 | 428614
12 | 20 | 6002526092 | KHAVDA 442MW | Service | Erection of MMS | SABNAM ENTERPRISE | SABNAM BANU | 2883657 | 423482
13 | 27 | 6002526110 | KHAVDA 442MW | Service | Erection of MMS | Polyvision India | Mahesh Ganesh Patel (9819343954) | 1156520 | 300000
14 | 29 | 6002526112 | KHAVDA 442MW | Service | Erection of MMS | M/S NITYA DEV ENTERPRISES | SANDEEP KUMAR (+91 9992279349, 9467496874) | 236952 | 209366
15 | 30 | 6002526113 | KHAVDA 442MW | Service | AC-DC Work | TD ELECTRICAL & SOLAR | TAPOMOY DEY: +91 7602143142 | 2280000 | 150000
16 | 31 | 6002526115 | KHAVDA 442MW | Service | Erection of MMS | Mahadev Infratech Enterprises | Hari Ram 9983414884, 8239971600 | 555841 | 100361
17 | 32 | 6002526120 | KHAVDA 442MW | Service | LT & Earthing Trench Work | R.K.PROJECT | GAGAL RAMESHBHAI (+91 6354263514) | 0 | 608934 |  |  |  | Entire Payment Pending
18 | 36 | 6002526132 | KHAVDA 442MW | Service | Hiring of Vechile | R.S.B.T. SUPPLIERS | Praveen bhalothia (+91 6005289994, 9879393598) | 1458428 | 496440
19 | 41 | 6002526145 | KHAVDA 442MW | Service | Erection of MMS | OZONE INFRA | AMIT KUMAR BAJPAI (+91 9554523222) | 1635481 | 908870
20 | 43 | 6002526152 | KHAVDA 442MW | Service | Erection of MMS | TANSUMAN LIGHTNING ENTERPRISES (OPC) PRIVATE LIMITED | Vishal Rathore (+91 7790909130) | 446072 | 111519
21 | 51 | - | KHAVDA 442MW | Supplier | Hardware & Machine | Rajkot Machinery | Rajkot Machinery | 1100000 | 130023 |  |  |  | Supplier Account
22 | 57 | - | KHAVDA 442MW | Service | Hiring Splicing Service | New Radiant Enterprises | New Radiant Enterprises | 0 | 61950 |  |  |  | Entire Payment Pending
23 | 5 | 6002526034 | KHAVDA 442MW | Service | IDT Civil | Dayachand -7 | PAWAN KUMAR 80555 27414 | 2740748 | 152263 |  |  |  | Highlighted Yellow in Statement
24 | 7 | 6002526064 | KHAVDA 442MW | Service | IDT Civil | Baburam-3 | BABU RAM (+91 9001678721) | 1160379 | 128931
25 | 20 | 6002526001 | KHAVDA 442MW | Service | AC-DC Work | J.P. ENTERPRISES | JAI PRAKASH +91 98282 39611 | 3535000 | 200000
26 | 42 | 6002526027 | KHAVDA 442MW | Service | HT Jointer | Sanjay Kumar Yadav | Sanjay Kumar Yadav | 700000 | 42306
27 | 50 | 6002526086 | KHAVDA 442MW | Service | Erection of MMS | SARTHAK ENTERPRISES | OM PRAKASH +91 8950588873, 9896098873 | 17118 | 4280
28 | 77 | 6002526136 | KHAVDA 442MW | Service | AC-DC Work | FATIMA CONSTRUCTION | ZAINAB FATMA 7428270013 | 2200000 | 450000
29 | 91 | 6002526155 | KHAVDA 442MW | Service | String Work | FATA RAM | FATA RAM (+91 8401688194) | 380700 | 42300
30 | 95 | 6002526159 | KHAVDA 442MW | Service | Erection of Module | Juhi Gulab | ALHANOOR (+91 8460311858) | 329386 | 93056 |  |  |  | Highlighted Yellow in Statement
31 | 135 | - | KHAVDA 442MW | Service | AC-DC Work | Nagnararai Construction Company-2 | Lun Singh ( 9680881351) | 3220000 | 700000
32 | 140 | - | KHAVDA 442MW | Service | HT Cable laying | Ashok Kumar Bairwa | Ashok Kumar Bairwa(9740523254) | 350248 | 25000
33 | 143 | - | KHAVDA 442MW | Service | Supply Labour | Girdhari Ram Labour | Girdhari Ram Labour | 821512 | 300000
34 | 147 | - | KHAVDA 442MW | Service | DC Works | Sumer Singh | Devi Singh/ Sumer Singh | 1961000 | 700000
35 | 154 | - | KHAVDA 442MW | Service | AC-DC Work | Jeeshan Ahemad | Jeeshan Ahemad | 1625000 | 100000
36 | 157 | - | KHAVDA 442MW | Service | Hiring of Vechile | SHARDA MAHALA | RJ37-GB-0907 | 73548 | 52903
37 | 158 | - | KHAVDA 442MW | Service | AC Work | Abhishek Pandey | Abhishek Pandey | 1495000 | 200000
38 | 159 | - | KHAVDA 442MW | Service | AC-DC Work | ISHAN | Sajjirul | 2100000 | 260000
39 | 173 | - | KHAVDA 442MW | Service | WATER SUPPLIERS | Abdul Kayum Ibrahim Sama | Abdul Kayum Ibrahim Sama | 300000 | 170000
40 | 177 | - | KHAVDA 442MW | Service | Erection of MMS | JAHANGIR ALI | JAHANGIR ALI | 179000 | 45861
41 | 182 | - | KHAVDA 442MW | Service | Oger Machine | Padam Singh | Padam SIngh | 0 | 39800 |  |  |  | Entire Payment Pending
42 | 185 | - | KHAVDA 442MW | Service | Hiring of Vechile | Mohan Lal | Mohan Lal | 0 | 40000 |  |  |  | Entire Payment Pending
43 | 186 | 6002627006 | KHAVDA 442MW | Service | Hiring of Vechile | TAJMAMAD LATIF SAMA | TAJMAMAD LATIF SAMA | 0 | 40000 |  |  |  | Entire Payment Pending
44 | 187 | - | KHAVDA 442MW | Service | Cabin / Material | Gujrat Pota Cabin | Gujrat Pota Cabin | 0 | 700000 |  |  |  | Entire Payment Pending
GRAND TOTAL (KHAVDA 442MW STATEMENT) | [11 empty] | RECONCILED | All 44 Records Verified

## Scope & Payment Summary
KHAVDA 442MW — SCOPE OF WORK SUMMARY & PAYMENT BREAKDOWN
Scope / Description | Vendor Count | Total Paid As On (₹) | Total Payable (₹) | Total Contract Value (₹) | Paid %
Erection of MMS
AC-DC Work
IDT Civil
Hiring of Vechile
HT Cable laying
Piling Work
Supply Of White Sand
DG
VLF Testing
LT & Earthing Trench Work
Hardware & Machine
Hiring Splicing Service
HT Jointer
String Work
Erection of Module
Supply Labour
DC Works
AC Work
WATER SUPPLIERS
Oger Machine
Cabin / Material
TOTALS